## Release Plan
Release | Features Included | Duration | Outcome
Release 1.0 | Model training | 2 days | Trained model was ready
Release 2.0 | Frontend simple basic UI | 3 days | Simple UI was ready
Release 3.0 | Backend and API connection. | 1 week | Predicting Result
Release 4.0 | Documentation, Testing, Deployment | 1 week | Final product

## Sprint Plan
Sprint | Duration | Tasks | Deliverables
Sprint 1 | Week 1 | Dataset setup, Train/Test split, Model training | CNN Model
Sprint 2 | Week 2 | Frontend UI | UI
Sprint 3 | Week 3 | Backend API creation, Integrate model, Test API | Fast API
Sprint 4 | Week 4 | Docs, Test plan, Video prep | Ready Product

## Task List
Task ID | Task Name | Description | Owner | Estimated Time(approx) | Status
T1 | Dataset Preparation | Download, clean, split dataset | ML Engineer | 6 hrs | Done
T2 | Model Training | Train CNN model, tune accuracy | ML Engineer | 10 hrs | Done
T3 | Backend Setup | FastAPI, load model, build routes | Backend Developer | 8 hrs | Done
T4 | Prediction API | Implement /predict endpoint | Backend Developer | 5 hrs | Done
T5 | Frontend UI | HTML upload page + preview | Frontend Developer | 6 hrs | Done
T6 | Integration | Connect UI → Backend → Model | Backend Developer | 6 hrs | Done
T7 | Design Docs | Architecture, flowcharts, DB schema | Product Owner | 8 hrs | Done
T8 | Testing | Functional, invalid images | Product Owner | 4 hrs | Done
T9 | Documentation | PRS, Data Plan, User Guide | Product Owner | 8 hrs | Done
T10 | IA-2 Video | MVP demo recording | Product Owner | 2 hrs | Done